## Application
APPLICATION FOR PAYMENT | [7 empty] | PAGE ONE OF | 2 |  | PAGES
TO OWNER: |  |  | PROJECT:
| Jay Terkiana |  | Jay Immigration Lawyer Office
377 S Daniel Way,
| San Jose, CA 95128 | [7 empty] | Distribution to:
FROM CONTRACTOR: |  |  | SCOPE OF WORK: |  |  | APPLICATION NO: | 4 |  | X | OWNER
| Bains Developments Commercial |  | Jay Immigration Lawyer Office |  |  | APPLICATION DATE: | 2022-10-03 |  |  | ARCHITECT
| 980 Mission Ct. |  |  |  |  | PAYMENT TERM: | Due on receipt |  |  | CONTRACTOR
| Fremont, CA 94539 |  |  |  |  | JOB NO: | 03011 |  |  | FILE
CONTRACT FOR:
CONTRACTOR'S APPLICATION FOR PAYMENT |  |  |  |  | The undersigned Contractor certifies that to the best of the Contractor's knowledge,
Application is made for payment, as shown below, in connection with the Contract. |  |  |  |  | information and belief the Work covered by this Application for Payment has been
Continuation Sheet is attached. |  |  |  |  | completed in accordance with the Contract Documents, that all amounts have been paid by
the Contractor for Work for which previous Certificates for Payment were issued and
payments received from the Owner, and that current payment shown herein is now due.
1. ORIGINAL CONTRACT SUM |  |  | $ | 781782
2. Net change by Change Orders |  |  | $ | 54132 | CONTRACTOR:
3. CONTRACT SUM TO DATE (Line 1 ± 2) $ |  |  | $ | 835914
4. TOTAL COMPLETED & STORED TO |  |  | $ | 518160.63
DATE (Column G on G703) |  |  |  |  | By: | Vagish Kapila |  |  | Date: |  | 2022-10-03
5. RETAINAGE:
a. | 10 | % of Completed Work $ | 0 |  | State of: |  |  | County of:
| (Column D + E on G703) |  |  |  | Subscribed and sworn to before me this |  |  | day of
b. |  | % of Stored Material $ |  |  | Notary Public:
| (Column F on G703) |  |  |  | My Commission expires:
Total Retainage (Lines 5a + 5b or
| Total in Column I of G703) |  | $ | 0 | CERTIFICATE FOR PAYMENT
6. TOTAL EARNED LESS RETAINAGE |  |  | $ | 518160.63 | In accordance with the Contract Documents, based on on-site observations and the data comprising the
| (Line 4 Less Line 5 Total) |  |  |  | application, the Architect or Construction Manager certifies to the Owner that to the best of the
7. LESS PREVIOUS CERTIFICATES FOR |  |  |  |  | their knowledge, information and belief the Work has progressed as indicated,
PAYMENT (Line 6 from prior Certificate) |  |  | $ | 485890.63 | the quality of the Work is in accordance with the Contract Documents, and the Contractor
8. CURRENT PAYMENT DUE |  |  | $ | 32270 | is entitled to payment of the AMOUNT CERTIFIED.
9. BALANCE TO FINISH, INCLUDING RETAINAGE $ |  |  |  | 317753.37
| (Line 3 less Line 6) |  |  |  | AMOUNT CERTIFIED . . . . . . . . . . . $
CHANGE ORDER SUMMARY |  |  | ADDITIONS | DEDUCTIONS | (Attach explanation if amount certified differs from the amount applied. Initial all figures on this
Total changes approved |  |  |  |  | Application and onthe Continuation Sheet that are changed to conform with the amount certified.)
in previous billing by Owner |  |  | 21862 |  | ARCHITECT or CONSTRUCTION MANAGER:
Total approved this Billing |  |  | 32270 |  | By: |  |  |  | Date:
TOTALS |  |  | 54132 | 0 | This Certificate is not negotiable. The AMOUNT CERTIFIED is payable only to the
Contractor named herein. Issuance, payment and acceptance of payment are without
NET CHANGES by Change Order |  |  | 54132 |  | prejudice to any rights of the Owner or Contractor under this Contract.

## Continuation Sheet
CONTINUATION SHEET | [7 empty] | PAGE OF PAGES |  | /WGPD
APPLICATION FOR PAYMENT, containing | [6 empty] | APPLICATION NO: | 4 |  | /wir.{d 25}~{r 6}/cf~~{L 6}~
Contractor's signed certification is attached. | [6 empty] | APPLICATION DATE: | 2022-10-03 |  | /wgpe
In tabulations below, amounts are stated to the nearest dollar. | [6 empty] | JOB NO: | 03011 |  | /ru.{d 26}
Use Column I on Contracts where variable retainage for line items may apply. | [9 empty] | {L 5}
{L 9}
A | B | C | D | E | F | G |  | H | I | /ru.{d 26}~
ITEM NO. | DESCRIPTION OF WORK | SCHEDULED VALUE | WORK COMPLETED |  | MATERIALS | TOTAL | % | BALANCE | RETAINAGE
|  |  | FROM PREVIOUS | THIS PERIOD | PRESENTLY | COMPLETED | (G ÷ C) | TO FINISH | (IF VARIABLE
|  |  | APPLICATION |  | STORED | AND STORED |  | (C - G) | RATE)
|  |  | (D + E) |  | (NOT IN | TO DATE
[5 empty] | D OR E) | (D+E+F)
1 | Temporary Construction | 410 | 410 |  |  | 410 | 100% |  | 0
2 | Site Work & Demolition | 33746 | 33746 |  |  | 33746 | 100% |  | 0
3 | Concrete | 41370 | 39301.5 |  |  | 39301.5 | 95% | 2068.5 | 0
4 | Steel/Masonry/Structural | 22241 | 8896.4 |  |  | 8896.4 | 40% | 13344.6 | 0
5 | Carpentry | 10710 | 3748.5 |  |  | 3748.5 | 35% | 6961.5 | 0
6 | Wood / Plastics | 19085 |  |  |  |  | 0% | 19085 | 0
7 | Thermal/ Moisture Protect | 3451 |  |  |  |  | 0% | 3451 | 0
8 | Doors / Glass | 49805.7 | 17930.052 |  |  | 17930.052 | 36% | 31875.648 | 0
9 | Finishes - Walls/Frames/Ceiling/Painting (Interior Metal Stud Framing) | 106675.9 | 34136.288 |  |  | 34136.288 | 32% | 72539.612 | 0
11 | Specialities (Accessories/Fire Alarm/Hood) | 17697 | 5309.1 |  |  | 5309.1 | 30% | 12387.9 | 0
12 | Equipment | 1600 |  |  |  |  | 0% | 1600 | 0
13 | Furnishings/Trash Removal | 7177.5 | 7177.5 |  |  | 7177.5 | 100% |  | 0
14 | Mechanical | 202797 | 162237.6 |  |  | 162237.6 | 80% | 40559.4 | 0
15 | Plumbing | 11209.2 | 2802.3 |  |  | 2802.3 | 25% | 8406.9 | 0
16 | Electrical | 161525.8 | 113068.06 |  |  | 113068.06 | 70% | 48457.74 | 0
17 | Fire Life Safety | 6268 |  |  |  |  | 0% | 6268 | 0
18 | General Conditions (GA, Superintendent, PM, Office, Admin. Etc) | 26413 | 10829.33 |  |  | 10829.33 | 41% | 15583.67 | 0
19 | General Liability Insurance | 25347 | 10392.27 |  |  | 10392.27 | 41% | 14954.73 | 0
20 | Contractor's Fee | 34253 | 14043.73 |  |  | 14043.73 | 41% | 20209.27 | 0
21 | Approved Additional Tag 1A - Mechanical | -147685 | -147685 |  |  | -147685 | 100% |  | 0
22 | Approved Additional Tag 2A - Asbestos | 22356 | 22356 |  |  | 22356 | 100% |  | 0
23 | Approved Additional Tag 3A - Mechanical 1 unit added | 35327 | 35327 |  |  | 35327 | 100% |  | 0
24 | Approved Additional Tag 4A - Framing, Tiles / Shower Fixtures, plumbing | 8868 | 8868 |  |  | 8868 | 100% |  | 0
25 | Approved Additional Tag 5B - Asbestos Abatement Additional Walls | 10889 | 10889 |  |  | 10889 | 100% |  | 0
26 | Approved Additional Tag 6A - Demo for Asbestos additional walls added | 15953 | 15953 |  |  | 15953 | 100% |  | 0
27 | Approved Additional Tag 7A - Demo 2nd Floor / Concrete new power,Floor drains / Mechanical Front Office / Exterior Painting | 76154 | 76154 |  |  | 76154 | 100% |  | 0
28 | Approved Additional Tag 8A | 32270 |  | 32270 |  | 32270 | 100% |  | 0
|  |  |  | 0 |  |  | #DIV/0!
| GRAND TOTALS | 835914.1 | 485890.63 | 32270 | 0 | 518160.63 | 61.99% | 317753.47 | 0